## Year 1 Budget
Category | Name | Hours | Rate | Total
Principal Investigator | Person 5 | 936 | 66 | 61776
Senior Software Developer | Person 1 | 1040 | 70 | 72800
Software Developer | Person 2 | 1040 | 25 | 26000
Audio Engineer | Person 3 | 387 | 20 | 7740
Artist | Person 4 | 906 | 40 | 36240
Lead Designer | Person 6 | 687 | 50 | 34350
Research Assistants |  | 342 | 15 | 5130
244036
Fringe benefits |  |  |  | 45565
Salaries |  |  |  | 289601
Travel |  |  |  | 5730
Supplies |  |  |  | 3600
TOTAL |  |  |  | 298931
| per diem | days | car | flight/mileage
North Dakota | 136 | 3 | 125 | 700 | 1233 | 3699
DC | 548 | 3 | 50 | 600 | 1198 | 1198
NIEA | 133 | 4 | 50 | 650 | 833 | 833
0.43558
8587.5
18200
6500

## tasks and schedule
Obj | Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
ALL | Obtain IRB approval | bar: 1
1.1 | Complete game design document | bar: 1
1.2 | Complete 12 commercial quality game levels | bar: 1 to 6
1.3 | Expand levels to allow greater individualization | bar: 3 to 7
1.4 | Create 9 in-game decision-making problems | bar: 1 to 5
1.5 | Create 36 in-game animated video clips | bar: 1 to 5
2.1 | Create 24 interactive journal activities | bar: 1 to 7
2.2 | Implement text messaging feature | bar: 3
3.1 | Create forms and database for data collection | bar: 3 to 5
3.2 | Write programs to score standardized measures | bar: 5
4.1 | Recruit sample | bar: 2
4.2 | Collect usability data | bar: 3 to 4
4.3 | Analyze usability data | bar: 4 to 5
ALL | Write interim and final reports | bar: 4; 8
5.1 | Program modifications to optimize performance | bar: 1 to 2
6.1 | Create multi-media online orientation | bar: 4
6.2 | Create virtual library of support resources | bar: 3 to 6
7.1 | Collect baseline and outcome data | bar: 5 to 7
7.2 | Recruit sample | bar: 5
7.3 | Conduct statistical analysis | bar: 8
#REF!

## Hours year 1
Task | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | total |  | Total
Obtain IRB approval |  |  |  |  | 24 |  |  | 24 |  | 24 | 24
Complete game design document | 20 | 40 | 12 | 18 | 12 | 480 |  | 582 |  | 588 | 1080
Complete 12 commercial quality game levels | 720 | 720 | 300 | 600 | 400 | 80 | 300 | 3120 |  | 6840 | 120
Expand levels to allow greater individualization | 72 | 70 | 16 | 90 | 40 | 20 |  | 308 |  | 530 | 12
Create 9 in-game decision-making problems |  | 24 | 8 | 9 | 60 | 12 | 6 | 119 |  | 148 | 288
Create 36 in-game animated video clips |  | 24 | 24 | 160 |  | 24 | 18 | 250 |  | 396 | 12
Create 24 interactive journal activities | 48 | 64 | 18 | 9 | 96 | 36 | 18 | 289 |  | 432
Implement text messaging feature | 48 |  |  |  | 16 |  |  | 64 |  | 64
Create forms and database for data collection | 40 |  |  |  | 20 | 8 |  | 68 |  | 84
Write programs to score standardized measures | 0 |  |  |  | 0 |  |  | 0 |  | 80
Recruit sample |  |  |  |  | 40 |  |  | 40 |  | 40
Collect usability data |  |  |  |  | 96 |  |  | 96 |  | 120
Analyze usability data |  |  |  |  | 40 |  |  | 40 |  | 80
Write interim and final reports |  |  |  |  | 40 |  |  | 40 |  | 80
Program modifications to optimize performance | 80 | 60 |  |  |  | 10 |  | 150 |  | 170 | 24
Create multi-media online orientation |  | 20 | 9 | 12 | 32 | 9 |  | 82 |  | 208 | 8
Create virtual library of support resources | 12 | 18 |  | 8 | 20 | 8 |  | 66 |  | 88
Collect baseline and outcome data |  |  |  |  | 0 |  |  | 0 |  | 160
Recruit sample |  |  |  |  | 0 | 0 |  | 0 |  | 60
Conduct statistical analysis |  |  |  |  | 0 | 0 |  | 0 |  | 80 | 1568
| 1040 | 1040 | 387 | 906 | 936 | 687 | 342 | 5338
Rate person | 70 | 25 | 20 | 40 | 66 | 50 | 15
| 72800 | 26000 | 7740 | 36240 | 61776 | 34350 | 5130 |  | 244036